PROPOSAL: Predictive Malaria Surveillance Using Integrated DHIS2-Climate Analytics

A Feasibility Study for AI-Augmented Outbreak Detection in Malawi

Submitted to: WHO Regional Office for Africa (AFRO) / TDR Joint Impact Grants for Regional Priorities
Deadline: 15 September 2026
Principal Investigator: [To be determined — Malawian researcher at University of Malawi College of Medicine or Public Health Institute of Malawi]
Institution: [Malawian academic institution or PHIM]
Total Budget Requested: US$14,850
Study Duration: 12 months (October 2026 – September 2027)
Research Priority: Priority 2 (Digital Health, AI-Supported Tools) + Priority 3 (Climate-Sensitive Diseases, Surveillance Strengthening)

1. SUMMARY

Malawi reports 21,000–33,000 malaria cases weekly, with outbreaks concentrated in the southern lowlands during the rainy season (November–April). Current surveillance through DHIS2 is reactive: districts detect outbreaks only after facility reports spike. The Public Health Institute of Malawi (PHIM) has explicitly identified “strengthening the linkage between signal detection and rapid field response” as a top priority.

This implementation research study will test whether a lightweight machine learning model, integrating existing DHIS2 weekly epidemiological data with open-source climate variables (rainfall, temperature, humidity), can predict malaria outbreaks at the Traditional Authority (TA) level 2–4 weeks in advance of current reactive detection. The study will be conducted in Nsanje District, a high-burden, flood-prone district in southern Malawi currently experiencing a measles outbreak and recurrent cholera — demonstrating the broader applicability of predictive surveillance for climate-sensitive diseases.

The study will generate: (a) a validated predictive model with accuracy metrics, (b) a district-level alert protocol with pre-calibrated thresholds, (c) a policy brief for PHIM and the Ministry of Health, and (d) peer-reviewed publication — providing the evidence base for national scale-up of AI-augmented surveillance as part of the broader Zisamale platform vision.

Keywords: malaria, predictive surveillance, machine learning, DHIS2, climate health, implementation research, Malawi

2. BACKGROUND AND PROBLEM STATEMENT

2.1 The Malaria Burden in Malawi

Malaria remains the leading cause of morbidity and mortality in Malawi, generating 21,000–33,000 cases weekly nationally. The southern region — particularly Nsanje, Neno, and Chikwawa districts — bears a disproportionate burden due to low elevation, high rainfall, and limited health infrastructure.

2.2 Surveillance Gap: Reactive vs. Predictive

Malawi uses DHIS2 as its national Health Management Information System, with weekly epidemiological reporting from all health facilities. While national reporting completeness is 95.3% and timeliness 94.7%, the system remains fundamentally reactive: - Districts detect outbreaks 1–2 weeks after case counts exceed thresholds. - No systematic integration of climate data (rainfall, temperature, flooding) into epidemiological forecasting. - District Rapid Response Teams (DRRTs) lack lead time to pre-position commodities (ACTs, RDTs, IV artesunate) or mobilize communities.

PHIM’s weekly surveillance bulletins repeatedly emphasize that “strengthening the linkage between signal detection and rapid field response remains a top priority.”

2.3 The Climate-Health Nexus

Malaria transmission in Malawi is strongly climate-driven. The rainy season (November–April) creates breeding sites for Anopheles mosquitoes. El Niño events and tropical cyclones trigger both flooding and malaria surges. The DHIS2 Climate & Health tools, recently launched in Malawi, provide a nascent infrastructure for integrating meteorological data — but no predictive models have been validated for operational use.

2.4 The Policy Window

Malawi’s National Health Policy (2023–2030) targets reducing malaria incidence and improving emergency preparedness. The TDR Strategy 2024–2029 explicitly calls for “country-led implementation research to strengthen health systems and address emerging global health challenges such as climate change.” This study directly bridges these policy priorities with actionable, context-specific evidence.

2.5 The Zisamale Vision

This $15,000 feasibility study is the proof-of-concept phase for Zisamale (“let us be well” in Chichewa) — a proposed $9.85M integrated AI-augmented community health intelligence platform. Zisamale’s three engines are: 1. MAMA-AI: Maternal and child health risk stratification for CHWs 2. ULALO-AI: Predictive disease surveillance (the focus of this study) 3. CHUMA-AI: Supply chain and referral intelligence

This study validates the core ULALO-AI prediction model, generating the peer-reviewed evidence required for the full Zisamale platform proposal.

3. OBJECTIVES

Primary Objective

To develop and validate a machine learning model that predicts malaria outbreaks at the Traditional Authority level in Nsanje District, Malawi, 2–4 weeks in advance, using integrated DHIS2 epidemiological data and open-source climate variables.

Secondary Objectives

- To assess the feasibility of integrating climate data into routine DHIS2 surveillance workflows at the district level.

- To identify implementation barriers and facilitators to acting on predictive alerts among District Health Office staff and DRRT members.

- To develop a pre-calibrated alert protocol with recommended response actions for district-level decision-makers.

- To strengthen local research capacity by training a Malawian Master’s-level data scientist in climate-health predictive modeling.

- To generate the evidence base for the ULALO-AI engine of the Zisamale platform.

4. RESEARCH QUESTIONS

- What is the predictive accuracy (sensitivity, specificity, PPV, NPV, AUC-ROC) of a DHIS2-climate integrated model for forecasting malaria outbreaks at the TA level in Nsanje District, 2–4 weeks in advance?

- What are the barriers and facilitators to district-level adoption of predictive surveillance alerts among DHO staff, clinicians, and DRRT members?

- What pre-calibrated alert thresholds and response protocols are most acceptable and actionable for district decision-makers?

5. STUDY DESIGN AND METHODS

5.1 Study Design

Mixed-methods implementation research study with three components: - Component A: Retrospective model development and validation (quantitative) - Component B: Prospective alert testing and accuracy assessment (quantitative) - Component C: Qualitative assessment of implementation barriers and facilitators (qualitative)

5.2 Study Site

Nsanje District, Southern Region, Malawi. Rationale: - High malaria burden with clear seasonality. - Current measles outbreak demonstrates surveillance system stress. - Flood-prone (Shire River valley) — ideal for climate-disease modeling. - Single district hospital (Nsanje District Hospital) and 15 health centres — manageable scope for validation. - Strong existing DHIS2 reporting infrastructure.

5.3 Component A: Retrospective Model Development (Months 1–4)

Data Sources: - DHIS2: Weekly malaria case counts (confirmed + suspected), severe malaria admissions, and RDT/ACT stock data from Nsanje District facilities, January 2019–September 2026. Extracted via DHIS2 API with MoHP authorization. - Climate Data: - CHIRPS daily rainfall (0.05° resolution, free, open-source) - MODIS/LST land surface temperature (free, open-source) - ERA5 reanalysis humidity and wind speed (free, open-source) - Flood extent data from UN OCHA/SERVIR (event-based) - Population Data: National Statistical Office projections by TA.

Model Development: - Outcome variable: Malaria outbreak defined as weekly confirmed cases exceeding the 90th percentile of the district’s historical distribution for that epidemiological week, adjusted for population. - Predictor variables: - Lagged malaria case counts (1–8 weeks) - Lagged rainfall (1–8 weeks, cumulative and intensity) - Lagged temperature and humidity (1–4 weeks) - Flood events (binary, 0–4 weeks lag) - Seasonal indicators (month, year) - TA-level population density - Models tested: - Seasonal ARIMA with exogenous climate variables (baseline) - Gradient-boosted machine (XGBoost/LightGBM) — primary - Long Short-Term Memory (LSTM) neural network — exploratory - Validation: Time-series cross-validation (rolling origin). Train on 2019–2023; validate on 2024–2025; test on 2026 prospective data.

Outputs: - Model performance metrics at 2-week and 4-week prediction horizons. - Variable importance analysis (which climate variables drive predictions?). - TA-level risk maps for Nsanje District.

5.4 Component B: Prospective Alert Testing (Months 5–9)

Procedure: - Deploy the validated model to generate weekly predictive alerts for Nsanje DHO during the 2026–2027 rainy season (November 2026–April 2027). - Each Monday, the model generates a TA-level risk score (1–10) and a binary “alert” flag for the coming 2–4 weeks. - Alerts are shared with the DHO surveillance officer and DRRT lead via email and WhatsApp. - Blinded validation: The DHO is asked to continue standard surveillance and document any outbreak responses. The study team independently tracks actual malaria case counts from DHIS2. - At the end of the season, compare: - Model predictions vs. actual outbreaks (prospective accuracy) - Whether DHO acted on alerts (implementation fidelity) - Time saved in outbreak detection vs. reactive DHIS2 thresholds

Outputs: - Prospective sensitivity, specificity, PPV, and NPV. - Alert response rate and reasons for non-response. - Time-to-detection comparison: predictive vs. reactive.

5.5 Component C: Qualitative Implementation Assessment (Months 6–10)

Participants: - 8–10 key informants: DHO surveillance officer, DRRT lead, district health officer, 2–3 facility in-charges, 2–3 community health workers, 1 PHIM surveillance officer. - 2 focus group discussions: DRRT members (6–8 per FGD) and community health workers (6–8 per FGD).

Methods: - Semi-structured interviews using an implementation science framework (Consolidated Framework for Implementation Research — CFIR). - Topics: data trust, alert usefulness, workload impact, resource constraints, decision-making authority, integration with existing workflows. - Interviews conducted in English or Chichewa by trained research assistants; recorded, transcribed, and translated.

Analysis: - Thematic analysis using NVivo or manual coding. - CFIR domains: intervention characteristics, outer setting (policy), inner setting (DHO culture), individuals (staff capacity), process (implementation).

Outputs: - Barrier/facilitator map for predictive surveillance adoption. - Recommendations for alert protocol design and DHO workflow integration.

5.6 Component D: Alert Protocol Development (Months 8–11)

- Convene a stakeholder workshop with DHO staff, DRRT members, PHIM representatives, and MoHP policymakers.

- Present model accuracy results and qualitative findings.

- Co-design a pre-calibrated alert protocol:

  - Green (risk score 1–3): Routine surveillance

  - Yellow (4–6): Enhanced community mobilization, pre-position RDTs/ACTs at health centres

  - Red (7–10): Activate DRRT, deploy outreach teams, request emergency commodity buffer from Central Medical Stores

- Draft policy brief for PHIM and MoHP.

6. EXPECTED OUTCOMES AND DELIVERABLES

Scientific Outputs

- Peer-reviewed publication in Malaria Journal or BMC Public Health (open access) — “Machine learning integration of DHIS2 and climate data for predictive malaria surveillance in rural Malawi: a mixed-methods implementation study.”

- Conference presentation at the 2027 ASTMH Annual Meeting or the WHO AFRO Regional Committee.

Policy Outputs

- Policy Brief for PHIM and MoHP: “Toward Predictive Surveillance in Malawi: Evidence from Nsanje District and Recommendations for National Scale-Up.”

- District Alert Protocol — a ready-to-use standard operating procedure (SOP) for DHOs.

Technical Outputs

- Open-source code repository (GitHub) with documented model scripts, data pipelines, and reproducible analysis workflow.

- Training manual for Malawian data scientists on climate-health predictive modeling using DHIS2 data.

Capacity Outputs

- One trained Master’s-level data scientist with peer-reviewed publication and practical ML-for-health experience.

- Strengthened DHO capacity in data interpretation and alert response.

Platform Outputs

- Validated ULALO-AI model ready for integration into the Zisamale platform.

7. INNOVATION AND SIGNIFICANCE

Why This Is Innovative

- First validated ML model for malaria prediction using Malawi’s DHIS2 data integrated with open climate data.

- Implementation-focused: Not just a technical proof-of-concept, but a study of whether predictions lead to action — the critical gap in digital health.

- Zero new infrastructure: Uses existing DHIS2 and free climate data, making it immediately replicable in other districts at near-zero marginal cost.

- Climate-health nexus: Directly addresses the intersection of climate change and infectious disease — a TDR Strategy 2024–2029 priority.

- Platform-anchored: Generates the evidence base for Zisamale, a scalable national platform.

Significance

- If successful, this study provides the evidence base for national scale-up of predictive surveillance across all 28 districts of Malawi as part of Zisamale.

- The open-source model and protocol can be adapted by other African countries using DHIS2 — directly supporting the TDR goal of “building on the African region’s experience.”

- The alert protocol can be incorporated into the National Malaria Strategic Plan and the Public Health Emergency Operations Center standard operating procedures.

8. ETHICAL CONSIDERATIONS

- Data Use: All DHIS2 data will be aggregated at the facility or TA level — no individual patient data. A data sharing agreement will be signed with the MoHP.

- Ethical Approval: Application to the National Health Sciences Research Committee (NHSRC) of Malawi will be submitted in Month 1.

- Community Engagement: District leadership and community leaders will be informed of the study purpose. No individual patient consent is required (aggregated data).

- Alert Ethics: During the prospective phase, the DHO retains full decision-making authority. Model alerts are advisory. A protocol ensures that missed alerts (false negatives) do not delay standard reactive surveillance.

- Data Protection: Compliance with Malawi’s Data Protection Act (2021). All datasets will be de-identified and stored on encrypted drives.

9. IMPLEMENTATION PLAN AND TIMELINE

| Month | Activities |
| --- | --- |
| 1 (Oct 2026) | NHSRC ethics submission; MoHP data sharing agreement; DHIS2 data extraction setup; climate data pipeline setup |
| 2 (Nov 2026) | Ethics approval; retrospective data extraction (2019–2025); baseline DHO workflow assessment |
| 3 (Dec 2026) | Data cleaning and integration; exploratory analysis; model architecture selection |
| 4 (Jan 2027) | Model training and validation; initial accuracy assessment; variable importance analysis |
| 5 (Feb 2027) | Prospective alert system deployment; DHO staff briefing; alert distribution begins |
| 6 (Mar 2027) | Mid-prospective data review; qualitative interviews begin (DHO, DRRT, CHWs) |
| 7 (Apr 2027) | Prospective alert period ends; data compilation; FGDs with DRRT and CHWs |
| 8 (May 2027) | Qualitative transcription and analysis; preliminary quantitative results |
| 9 (Jun 2027) | Integrated analysis; draft policy brief and alert protocol |
| 10 (Jul 2027) | Stakeholder workshop (Nsanje); protocol finalization; policy brief revision |
| 11 (Aug 2027) | Manuscript drafting; code repository documentation; training manual completion |
| 12 (Sep 2027) | Final report submission; manuscript submission; knowledge dissemination |

10. BUDGET (US$14,850)

| Line Item | Unit Cost | Quantity | Duration | Total (USD) |
| --- | --- | --- | --- | --- |
| Personnel |  |  |  | $7,200 |
| Principal Investigator (20% FTE) | $800/month | 1 | 12 months | $1,920 |
| Research Assistant / Data Scientist (50% FTE) | $600/month | 1 | 12 months | $3,600 |
| Field Research Assistant (qualitative data collection) | $300/month | 1 | 4 months | $1,200 |
| Transcription/Translation (Chichewa–English) | $15/hour | 40 hours | 1 | $600 |
| Operations |  |  |  | $3,800 |
| Travel & transport (PI + RA to Nsanje, 6 round trips) | $200/trip | 12 trips | 1 | $2,400 |
| Fuel for field visits within Nsanje | $150/month | 1 | 6 months | $900 |
| Stakeholder workshop (venue, materials, refreshments, 20 participants) | $250 | 1 | 1 | $250 |
| Office supplies & communications | $250 | 1 | 1 | $250 |
| Technology & Data |  |  |  | $2,300 |
| Laptop for data scientist (1) | $800 | 1 | 1 | $800 |
| External hard drive (encrypted, 2TB) | $100 | 2 | 1 | $200 |
| Cloud computing credits (model training, AWS/Azure) | $150/month | 1 | 6 months | $900 |
| Statistical software license (Stata/SPSS or RStudio Cloud) | $200 | 1 | 1 | $200 |
| Mobile data for field connectivity | $50/month | 1 | 4 months | $200 |
| Dissemination |  |  |  | $1,050 |
| Open-access publication fee | $1,500 | 1 | 1 | $1,500 |
| Policy brief design & printing (100 copies) | $150 | 1 | 1 | $150 |
| Conference travel (regional, 1 presenter) | $1,200 | 1 | 1 | $1,200 |
| Contingency (5%) |  |  |  | $500 |
| TOTAL |  |  |  | $14,850 |

Co-funding: The PI’s institution will provide in-kind office space, internet, and administrative support. The DHO Nsanje will provide in-kind meeting space and staff time for interviews.

11. RESEARCH TEAM AND INSTITUTIONAL CAPACITY

Principal Investigator

[Name to be inserted]
- Affiliation: [University of Malawi College of Medicine / Public Health Institute of Malawi]
- Qualifications: [Master’s or PhD in Public Health, Epidemiology, or Biostatistics]
- Experience: [Implementation research training — TDR IR Toolkit or MOOC; DHIS2 data analysis experience; 3+ years in malaria/surveillance research]
- Publications: [2–3 relevant peer-reviewed publications]

Research Team

- Data Scientist: Master’s student in Biostatistics or Computer Science, with training in Python/R and machine learning.

- Field Research Assistant: Experienced qualitative researcher fluent in Chichewa and English.

- Technical Advisor: Senior biostatistician or epidemiologist (international or regional) with climate-health modeling experience — 5% FTE, in-kind or co-funded.

Institutional Support

- Host Institution: [Malawian university or PHIM] — provides office space, ethical oversight support, and institutional affiliation.

- Collaborating Institution: Nsanje District Health Office — provides facility access, DHIS2 data facilitation, and DHO staff participation.

- Policy Partner: Public Health Institute of Malawi (PHIM) — provides surveillance data access and policy dissemination pathway.

- Platform Partner: Zisamale Consortium — provides technical architecture guidance and integration pathway for scale-up.

Capacity Strengthening

- The Research Assistant (data scientist) will receive structured mentorship in: (a) time-series forecasting for epidemiology, (b) DHIS2 API data extraction, (c) climate data integration, and (d) academic writing. By project end, they will have a peer-reviewed publication and a trained skill set directly applicable to Malawi’s digital health workforce and the Zisamale platform.

12. MONITORING AND EVALUATION

| Indicator | Target | Data Source |
| --- | --- | --- |
| Ethics approval obtained | Month 1 | NHSRC certificate |
| Retrospective dataset compiled | Month 2 | Data inventory |
| Model validation AUC-ROC | >=0.75 | Model output |
| Prospective alerts generated | 20–25 weekly reports | Alert log |
| Qualitative interviews completed | 10 KIIs + 2 FGDs | Interview records |
| Policy brief submitted to PHIM | Month 10 | Submission receipt |
| Manuscript submitted to peer-reviewed journal | Month 12 | Journal submission confirmation |
| Data scientist trained and publication co-authored | Month 12 | CV update, publication authorship |
| ULALO-AI model validated for Zisamale integration | Month 12 | Technical validation report |

13. KNOWLEDGE TRANSLATION AND POLICY ENGAGEMENT

- Month 2: Present study protocol to Nsanje DHO and district stakeholders for buy-in.

- Month 6: Mid-term briefing to PHIM surveillance team with preliminary retrospective findings.

- Month 10: Stakeholder workshop in Nsanje to co-design alert protocol; distribute policy brief.

- Month 11: Present final results to MoHP Technical Committee and Parliamentary Health Committee.

- Month 12: Submit manuscript; present at regional conference; deposit code and data documentation in open repository; submit technical validation report to Zisamale Consortium for platform integration.

14. SUSTAINABILITY AND SCALE-UP PATHWAY

This $15,000 study is designed as the proof-of-concept phase for the Zisamale platform. The pathway is:

- Phase 1 (this grant): Validate the ULALO-AI model in one district. Generate evidence, protocol, and policy brief.

- Phase 2 (Gates-OpenAI / USAID / World Bank): Scale the validated model to 3–5 additional districts, integrate into DHIS2 dashboards, and deploy automated alerting as part of the full Zisamale platform. ($500K–$2M)

- Phase 3 (Government + GESD 2.0): National scale to all 28 districts, with PHIM assuming model maintenance and the alert protocol incorporated into national emergency SOPs. ($2M–$5M)

The policy brief and peer-reviewed publication from this study will be cited in the Zisamale grant proposals, dramatically increasing their credibility and likelihood of funding.

15. REFERENCES

- Ministry of Health and Population, Malawi. National Health Policy 2023–2030. Lilongwe: MoHP; 2023.

- Public Health Institute of Malawi. Weekly Epidemiological Surveillance Bulletin. Lilongwe: PHIM; 2026.

- TDR. Strategy 2024–2029: Research for Implementation. Geneva: WHO/TDR; 2024.

- WHO Regional Office for Africa. Implementation Research for Regional Priorities: Call for Applications 2026–27. Brazzaville: WHO AFRO; 2026.

- HISP UNIMA / GIZ. DHIS2 Climate & Health Project, Malawi. 2025–2027.

- [Additional references on malaria prediction models, DHIS2 climate integration, and implementation research frameworks to be added by PI.]

REQUIRED ATTACHMENTS (To Be Included in PDF)

- Acknowledgement Letter — Signed by the District Health Officer, Nsanje District Health Office, confirming support for the study and access to DHIS2 data.

- Ethical Approval — NHSRC certificate (to be obtained by Month 1; application submitted with proposal).

- CV of Principal Investigator — Maximum 1 page, per call requirements.

- Institutional Support Letter — From the Dean/Director of the host institution confirming office space and administrative support.

- Data Sharing Agreement Draft — Between PI, host institution, and MoHP (template included).

- Zisamale Platform Concept Note — One-page overview of the broader platform vision, showing how this study fits into the integrated system.

Prepared for the WHO AFRO/TDR Joint Impact Grants for Regional Priorities
August 2026