ZISAMALE: The Malawi AI-Augmented Community Health Intelligence Platform

Full Concept Note & Detailed Budget Framework

Submitted to: Gates Foundation – OpenAI AI Health Initiative for Africa
Submission Date: August 2026
Total Request: $9,850,000 over 36 months
Implementing Consortium:
- Lead: Partners In Health (PIH) – Malawi
- Technical: VillageReach – Digital Health Division
- Research: Public Health Institute of Malawi (PHIM) / University of Malawi College of Medicine
- Government Partner: Ministry of Health and Population (MoHP), Republic of Malawi
- AI Technical Partner: [To be determined – open to OpenAI/Gates technical collaboration]

TABLE OF CONTENTS

- Executive Summary

- Competitive Landscape: What Already Exists

- Problem Statement & Context

- Proposed Solution

- Theory of Change

- Implementation Approach

- Monitoring, Evaluation & Learning (MEL)

- Sustainability & Scale-Up Plan

- Risk Analysis & Mitigation

- Detailed Budget Framework (36 Months)

- Annexes

1. EXECUTIVE SUMMARY

Malawi’s health system operates at only 45% of required staffing norms, with just 54% of health facilities delivering essential services. Maternal mortality remains at 439 per 100,000 live births, malaria generates 21,000–33,000 cases weekly, and the country is currently responding to a measles outbreak in Nsanje District. Meanwhile, Malawi has invested heavily in digital health infrastructure—DHIS2, iCHIS for Community Health Workers (CHWs), and the Community Health Toolkit (CHT)—yet these systems remain reactive rather than predictive.

Multiple well-funded initiatives are already deploying AI and predictive analytics in Malawi and across Africa. HISP UNIMA and GIZ are currently integrating climate data into DHIS2 for predictive surveillance in 4 Malawian districts (Dec 2025–Mar 2027). The Gates-Wellcome-Novo Nordisk EVAH initiative is funding CHW AI decision-support evaluations. VillageReach is optimizing AI-driven supply chains. Kenya is deploying AI across 100,000+ community health promoters. Nigeria and The Gambia have operational AI malaria prediction systems using DHIS2.

Zisamale (“let us be well” in Chichewa) does not pretend to be the first AI health platform in Malawi. It is designed to be the first integrated system that closes the loop between prediction, community action, supply chain response, and policy governance. Through three engines:

- MAMA-AI: Maternal and child health risk stratification for CHWs, generating dynamic risk scores and prioritized home visit lists.

- ULALO-AI: Predictive disease surveillance that ingests CHW symptom data, DHIS2 facility data, and climate variables to forecast outbreaks 2–4 weeks in advance.

- CHUMA-AI: Supply chain and referral intelligence that predicts medicine stockouts and optimizes patient referrals based on real-time facility capacity.

Zisamale integrates these three engines into a single, closed-loop system: predict → alert → deploy CHWs → resupply → measure outcome → retrain model. Critically, it is designed to generate the evidence base for Malawi’s first National AI in Health Policy Framework—positioning the country as a regional leader in ethical, effective AI deployment in low-resource settings.

Total funding requested: $9,850,000 over 36 months.

2. COMPETITIVE LANDSCAPE: WHAT ALREADY EXISTS

We are transparent about the competitive environment because funders will know it, and pretending otherwise destroys credibility. Here is what is already active in Malawi and the region:

2.1 Predictive Surveillance: HISP UNIMA / GIZ / DHIS2 Climate & Health (ACTIVE)

Status: Live, funded, government-backed. Launched December 2025, runs through March 2027.

What they do: - Integrate climate and health data into Malawi’s DHIS2 HMIS and One Health Surveillance Platform (OHSP) - Deploy the CHAP Modeling Platform for predictive modeling of climate-sensitive diseases - Generate climate-informed early warning alerts and dynamic risk maps - Facilitate interoperability with WHO’s EWARS system - Operating in 4 districts initially with plans to scale - Funded by BMZ/GIZ, implemented by HISP University of Malawi

What they do NOT do: - Push risk scores to CHWs for household-level intervention - Integrate predictions with supply chain pre-positioning - Have a policy pathway beyond “generate alerts” - Connect surveillance to community health action

Zisamale’s differentiation: ULALO-AI alerts automatically trigger MAMA-AI prioritized CHW visits AND CHUMA-AI stock pre-positioning. It is not surveillance for surveillance’s sake — it is surveillance that drives action.

2.2 CHW AI Decision Support: EVAH Initiative (ACTIVE)

Status: Funded and deploying. RFP launched March 2026 by Gates Foundation, Novo Nordisk Foundation, and Wellcome Trust.

What they do: - Pathway A: Up to $1M for real-world evaluation of early-deployment AI tools for frontline workers - Pathway B: Up to $3M for rigorous impact evaluations at scale - Focus: sub-Saharan Africa, South Asia, Southeast Asia - Evaluating AI-enabled decision support for primary and community health care

What they do NOT do: - Integrate CHW triage with national surveillance predictions - Build supply chain intelligence - Create policy architecture for national scale - Their projects are evaluations of isolated tools, not integrated systems

Zisamale’s differentiation: MAMA-AI risk scores are contextualized by ULALO-AI outbreak predictions. If malaria is predicted to surge in TA X next week, every pregnant woman and under-5 in TA X gets their risk score automatically elevated. The CHW triages with foresight, not just symptoms.

2.3 AI Supply Chain: VillageReach (ACTIVE)

Status: Active in Malawi, focused on maternal health supply chains.

What they do: - AI-driven supply chain optimization - Connected diagnostics - LMIS integration for commodity tracking

What they do NOT do: - Dynamically adjust orders based on predicted outbreak demand - Integrate with CHW risk stratification - Connect supply predictions to community health deployment

Zisamale’s differentiation: CHUMA-AI ingests ULALO-AI outbreak predictions as a demand signal. If malaria is predicted to spike in Nsanje in 3 weeks, CHUMA-AI automatically increases the recommended ACT/RDT order before the surge hits. It is demand-driven resilience, not inventory management.

2.4 Regional Competitors

| Project | Country | What They Do | Gap Zisamale Fills |
| --- | --- | --- | --- |
| Comoros AI-Driven Predictive Epidemiology | Comoros | AI monitoring and forecasting malaria using DHIS2 data | No CHW integration, no supply chain link |
| The Gambia AI Fusion | The Gambia | DHIS2 + climate data fusion for malaria prediction using XGBoost | No community action layer, no policy pathway |
| Nigeria SARIMAX / Femi Samson Institute | Nigeria | Seasonal ARIMA and AI malaria intelligence platform | No integrated CHW-supply chain loop |
| Kenya CHP AI (Causal Foundry) | Kenya | AI across 100,000+ community health promoters for clinical decision support | No predictive surveillance integration, no supply chain intelligence, no policy framework |

2.5 The Honest Conclusion

No one is doing all three as one integrated platform. Every competitor is building a tool. No one is building the system that connects prediction to community action to supply response to policy governance. Zisamale’s competitive advantage is not being first — it is being the first to build the institutional infrastructure that makes AI permanent in Malawi’s health system.

3. PROBLEM STATEMENT & CONTEXT

3.1 The Health System Crisis

Malawi is a low-income country of 20.4 million people, 80% of whom live in rural areas. The health system faces a perfect storm of challenges:

- Human Resources for Health (HRH) Crisis: Staffing stands at 45% of required norms. The doctor-to-population ratio is approximately 1:50,000. CHWs (Health Surveillance Assistants, or HSAs) are the de facto primary care providers for the rural majority, yet they lack tools to prioritize high-risk households or anticipate disease clusters.

- Maternal and Child Health Gaps: Maternal mortality is 439 per 100,000 live births. Under-5 mortality is 42 per 1,000 live births. Only 54% of facilities deliver the full package of essential services. Adolescent pregnancies account for 15% of maternal deaths.

- Infectious Disease Burden: Malaria remains the leading cause of morbidity and mortality, with 21,000–33,000 weekly cases. Cholera outbreaks are recurrent and climate-driven. Measles immunity gaps persist, as evidenced by the current Nsanje District outbreak (188 suspected cases).

- Supply Chain Failures: Medicine stockouts are chronic. The National Health Policy explicitly targets reducing stockouts to zero by 2030, but current logistics systems lack predictive capacity.

- Fragmented Health Financing: The system is highly donor-dependent, with inefficient resource allocation and limited domestic capacity for strategic health purchasing.

3.2 The Digital Health Foundation

Despite these challenges, Malawi possesses a surprisingly robust digital health infrastructure:

- DHIS2: The national Health Management Information System (HMIS), used for aggregate reporting across all health facilities.

- iCHIS (Integrated Community Health Information System): A CHT-based platform deployed to CHWs for household registration, pregnancy tracking, childhood illness management (iCCM), and event-based surveillance.

- YendaNafe: A proven CHT-based CHW app piloted in Neno District, demonstrating that CHWs can effectively adopt smartphone-based digital tools in rural Malawi.

- LMIS (Logistics Management Information System): Tracks commodity consumption and stock levels at facilities.

- DHIS2 Climate & Health Tools: Recently launched modules integrating meteorological data with disease surveillance.

- One Health Surveillance Platform (OHSP): A nascent platform for integrated human-animal-environmental health surveillance.

The critical gap is not data collection—it is intelligence and integration. These systems collect vast quantities of data but cannot transform it into predictive, actionable insights at the point of care or the district command center. More importantly, no existing system connects surveillance prediction to CHW deployment to supply chain response.

3.3 The Policy Window

Malawi’s National Health Policy (2023–2030) explicitly calls for digital health solutions to achieve its targets. The policy aims to: - Increase facilities delivering essential services from 54% to 100%. - Reduce medicine stockouts to zero. - Achieve 100% of staffing norms. - Improve health information systems and data use for decision-making.

Simultaneously, international funding for AI in African health has reached an inflection point. The Gates Foundation and OpenAI launched a $50M AI Health Initiative for Africa in January 2026, explicitly seeking projects that “build intelligence into existing systems” and generate evidence for national AI health policies.

Zisamale is designed to seize this policy window — not by claiming to be first, but by claiming to be the first to build the system that makes everything else work together.

4. PROPOSED SOLUTION

4.1 Vision

To transform Malawi’s community health system from reactive to predictive by building the first integrated human-AI hybrid system that closes the loop between surveillance, community action, supply chain response, and national policy governance.

4.2 The Three Engines

Engine 1: MAMA-AI — Maternal & Child Health Risk Stratification

Objective: Reduce maternal and under-5 mortality by enabling CHWs to identify and intervene with high-risk pregnancies and childhood illnesses before they become emergencies.

Functionality: - Dynamic Risk Scoring: An ML model ingests CHW-collected variables (maternal age, parity, obstetric history, danger signs, distance to facility, socioeconomic indicators, weather patterns) to generate a continuously updated risk score (1–10) for every pregnant woman and child under-5 in a CHW’s catchment area. - Contextualized by Surveillance: Risk scores are automatically adjusted when ULALO-AI predicts an outbreak in the CHW’s catchment area. A pregnant woman in a predicted malaria hotspot gets her risk score elevated even if her individual symptoms are mild. - Prioritized Home Visit Lists: The CHW app displays a daily prioritized list of households requiring visits, ranked by risk score and time-sensitivity. - iCCM Decision Support: For childhood illnesses, the AI assists CHWs in distinguishing cases manageable at the community level from those requiring immediate referral. - Tailored Counseling: The app generates context-specific counseling scripts based on the individual risk profile. - Referral Tracking: When a CHW refers a patient, the system tracks whether the patient reached the facility, and flags “lost to follow-up” cases.

Technical Approach: - Lightweight gradient-boosted models (XGBoost/LightGBM) running on-device for risk scoring, with periodic cloud model updates. - Edge-first architecture: critical triage decisions happen locally on the CHW’s device. - Federated learning approach: model improvements trained on aggregated, de-identified data.

Integration: - Bidirectional sync with iCHIS (CHW data) and DHIS2 (facility data). - Feeds pregnancy outcomes and childhood illness data into national HMIS in real time.

Engine 2: ULALO-AI — Predictive Surveillance & Outbreak Detection

Objective: Shift Malawi’s disease surveillance from reactive event detection to proactive outbreak prediction, enabling District Rapid Response Teams (DRRTs) to pre-position resources and mobilize communities before crises peak.

Functionality: - Multi-Stream Data Ingestion: - Community Stream: CHW-reported symptoms and cases from iCHIS. - Facility Stream: DHIS2 weekly epidemiological data, laboratory confirmations, and admission trends. - Climate Stream: Rainfall, temperature, humidity, and flood risk data from DHIS2 Climate & Health tools and meteorological APIs. - Predictive Modeling: - Malaria: Seasonal hotspot prediction at the Traditional Authority (TA) level, 2–4 weeks ahead. - Cholera: Water contamination risk mapping based on flood data, sanitation coverage, and historical outbreak patterns. - Measles: Immunity gap detection by analyzing vaccination coverage data and case clustering. - Diarrheal Disease: Cluster detection in under-5s using CHW symptom data and water source quality proxies. - Automated Alert System: When a model predicts an outbreak probability above a calibrated threshold, the system automatically generates alerts to DHO and DRRT with pre-populated response recommendations. - Closed-Loop Integration: Alerts do not sit in an inbox. They automatically: 1. Elevate MAMA-AI risk scores for all high-risk individuals in the predicted hotspot 2. Trigger CHUMA-AI to pre-position commodities in affected facilities 3. Log response actions for model retraining

Technical Approach: - Time-series forecasting models (ARIMA, Prophet, LSTM) for seasonal diseases. - Spatial clustering algorithms (DBSCAN, SaTScan) for outbreak detection. - Ensemble models combining climate, epidemiological, and community data streams. - Cloud-based analytics pipeline with automated report generation.

Integration: - Direct feed into DHIS2 and the One Health Surveillance Platform (OHSP). - Dashboard access for PHIM, DHOs, and the Ministry of Health Emergency Operations Center.

Engine 3: CHUMA-AI — Supply Chain & Referral Intelligence

Objective: Eliminate medicine stockouts and optimize patient referrals by matching patient needs with facility capacity in real time.

Functionality: - Demand-Driven Stockout Prediction: Predicts medicine stockouts 4–6 weeks in advance by analyzing LMIS consumption data, seasonality, ULALO-AI outbreak predictions, and supply chain lead times. A predicted malaria surge automatically increases the recommended ACT/RDT order. - Smart Referral Routing: When a CHW refers a patient, the system recommends the optimal facility based on distance, current stock of required medicines, staffing levels, and bed availability. - Ministerial Dashboard: An AI-powered policy dashboard that: - Forecasts district-level resource needs 3–6 months ahead - Models budget scenarios - Tracks National Health Policy target progress in real time - Generates natural-language executive summaries for non-technical policymakers

Technical Approach: - Demand forecasting models (seasonal ARIMA, gradient boosting) for commodity prediction. - Multi-criteria decision analysis for referral optimization. - Interactive web dashboard with automated natural language generation (NLG) summaries.

Integration: - Direct API integration with LMIS and DHIS2. - Ministerial dashboard hosted on government servers with appropriate cybersecurity protocols.

4.3 Platform Architecture

┌─────────────────────────────────────────────────────────────────┐
│                    ZISAMALE PLATFORM                             │
├─────────────────────────────────────────────────────────────────┤
│  CHW Layer (Android, Offline-First, CHT-Compatible)              │
│  ├── MAMA-AI: On-device risk scoring & triage                   │
│  │   └─ Contextualized by ULALO-AI outbreak predictions         │
│  ├── ULALO-AI: Symptom reporting & outbreak signal capture       │
│  └── CHUMA-AI: Referral initiation & medicine request           │
│       └─ Facility recommendations with real-time stock data      │
├─────────────────────────────────────────────────────────────────┤
│  District Layer (Cloud Analytics + DHIS2 Integration)            │
│  ├── ULALO-AI: Outbreak prediction & DRRT alerting            │
│  │   └─ Auto-triggers MAMA-AI risk elevation                   │
│  │   └─ Auto-triggers CHUMA-AI pre-positioning                 │
│  ├── CHUMA-AI: District supply chain optimization               │
│  └── DHIS2 Sync: Bidirectional data exchange                    │
├─────────────────────────────────────────────────────────────────┤
│  National Layer (Ministerial Dashboard + Policy Tools)           │
│  ├── CHUMA-AI: Resource forecasting & budget modeling           │
│  ├── ULALO-AI: National surveillance intelligence               │
│  └── Policy Evidence Base: Automated M&E reporting              │
└─────────────────────────────────────────────────────────────────┘
         ↑↓ CLOSED LOOP: Outcome data feeds back to model retraining

4.4 Ethical AI Framework

Zisamale will be governed by a rigorous ethical framework, developed in partnership with the MoHP and aligned with WHO guidance on AI in health:

- Transparency: All AI-driven recommendations will be explainable—CHWs and clinicians will see the key factors driving each recommendation.

- Fairness: Models will be audited for bias across demographic groups. Training data will be stratified to ensure representation of marginalized populations.

- Privacy: All patient data will be de-identified at the point of aggregation. Edge computing ensures sensitive data never leaves the device unnecessarily. Compliance with Malawi’s Data Protection Act (2021).

- Human-in-the-Loop: AI recommendations are advisory, not mandatory. CHWs and clinicians retain final decision-making authority.

- Accountability: A National AI Health Ethics Committee (to be established under PHIM) will review model performance, bias audits, and incident reports quarterly.

5. THEORY OF CHANGE

5.1 Logic Model

| Inputs | Activities | Outputs | Outcomes | Impact |
| --- | --- | --- | --- | --- |
| $9.85M funding; MoHP partnership; 3 pilot districts; existing DHIS2/iCHIS infrastructure; CHW workforce; climate data | Deploy MAMA-AI to 450 CHWs; deploy ULALO-AI to 3 DHOs; deploy CHUMA-AI to 45 facilities + MoHP; train 600 health workers; conduct implementation science research | 450 CHWs using AI-augmented tools; 3 districts with predictive surveillance; 45 facilities with stockout prediction; 1 ministerial dashboard; 1 national AI health policy framework drafted | ↑ CHW identification of high-risk pregnancies; ↓ maternal complications reaching facilities as emergencies; ↑ timeliness of outbreak response; ↓ medicine stockout duration; ↑ optimal referral matching | ↓ Maternal mortality; ↓ Under-5 mortality; ↓ Outbreak case fatality rates; ↓ Stockout-related treatment failures; ↑ National Health Policy target achievement |

5.2 Pathways to Policy Change

Pathway 1: Evidence → Guidelines - Rigorous MEL generates evidence that AI-augmented CHWs improve maternal/child outcomes without increasing workload. - Evidence packaged into policy briefs and presented to MoHP Health Technical Services Committee. - Result: Revised CHW scope of practice and iCCM guidelines incorporating AI decision support.

Pathway 2: Surveillance Intelligence → Emergency Preparedness - ULALO-AI demonstrates measurable improvements in outbreak detection timeliness and response pre-positioning. - PHIM adopts ULALO-AI as the standard for district-level surveillance. - Result: National AI Surveillance Standards incorporated into the Public Health Act.

Pathway 3: Ministerial Dashboard → Budget Allocation - CHUMA-AI dashboard demonstrates that predictive resource allocation reduces waste and improves service delivery. - Ministry of Finance and Ministry of Health use dashboard for budget planning. - Result: AI-informed health budgeting becomes standard practice; Performance-Based Grants incorporate AI-predicted indicators.

Pathway 4: Ethics Framework → National AI Policy - Zisamale Ethics Committee generates the first comprehensive framework for AI in health in Malawi. - Framework reviewed by Parliament and National Commission for Science and Technology. - Result: Malawi National AI in Health Policy Act — the first of its kind in Southern Africa.

6. IMPLEMENTATION APPROACH

6.1 Pilot District Selection

Three districts selected to represent Malawi’s epidemiological and geographic diversity:

| District | Profile | Population | Key Health Challenges | Rationale |
| --- | --- | --- | --- | --- |
| Nsanje | Rural, southern, lowland, flood-prone | 350,000 | High malaria burden; recurrent cholera; current measles outbreak; poor road infrastructure | Tests all three engines under extreme resource constraints; validates outbreak prediction in active emergency |
| Neno | Rural, highland, remote | 150,000 | High maternal mortality; limited facility access; strong existing CHW program (PIH/YendaNafe) | Builds on proven CHT infrastructure; tests referral optimization in district with only 1 hospital |
| Blantyre (rural TAs) | Peri-urban/peri-rural transition | 200,000 (rural TAs) | Mixed disease burden; higher facility density but overcrowding; adolescent health issues | Tests CHUMA-AI referral optimization where multiple facilities create choice complexity |

6.2 Implementation Phases

Phase 1: Foundation & Co-Design (Months 1–6)

- Formalize MoU with MoHP; establish Project Steering Committee chaired by Principal Secretary for Health.

- Conduct human-centered design workshops with 60 CHWs, 15 nurses, 9 DHO staff, and MoHP policymakers.

- Technical setup: cloud infrastructure, DHIS2 API integrations, baseline ML models using historical data.

- Submit research protocol to NHSRC; establish AI Ethics Committee.

- Conduct baseline household surveys in pilot districts.

Phase 2: Pilot Deployment (Months 7–18)

- Roll out MAMA-AI to 450 CHWs across 3 districts (150 per district).

- Deploy ULALO-AI dashboards to 3 DHOs and CHUMA-AI to 45 health facilities.

- Launch CHUMA-AI policy dashboard at MoHP.

- Conduct initial training; establish peer support networks and helpdesk channels.

- Monthly data review meetings; quarterly model retraining; continuous UX refinement.

Phase 3: Evaluation & Policy Development (Months 13–24)

- Conduct mixed-methods implementation science study.

- Present interim findings to MoHP Technical Committee, Parliamentary Health Committee, and National Commission for Science and Technology.

- Develop draft National AI in Health Policy, revised CHW scope of practice, and AI Surveillance Standards.

- Develop national scale-up plan and business case for government budget transition.

Phase 4: Transition & National Scale (Months 19–36)

- Transfer platform operations to PHIM and MoHP IT Division.

- Deploy to additional 5–7 districts using government and World Bank GESD 2.0 funding.

- Integrate maintenance costs into MoHP recurrent budget; establish Performance-Based Grant indicators.

- Host Southern Africa AI in Health Symposium in Lilongwe; publish implementation toolkit.

6.3 Consortium Roles

| Partner | Role | Key Responsibilities |
| --- | --- | --- |
| PIH – Malawi | Lead Implementer | Overall project management; CHW training and supportive supervision; community engagement; M&E data collection; government liaison |
| VillageReach | Technical Architect | Platform development and integration; DHIS2/iCHIS/LMIS API connectivity; cloud infrastructure; cybersecurity; technical support desk |
| PHIM / College of Medicine | Research & Evaluation | Implementation science study design and execution; model validation; bias auditing; policy evidence synthesis; ethics oversight |
| MoHP | Government Partner | Policy integration; regulatory approvals; data sharing agreements; scale-up mandate; budget transition |
| OpenAI / Gates Technical Partner | AI R&D Support | Model architecture consultation; edge AI optimization; natural language generation for policy summaries; ethics framework input |

7. MONITORING, EVALUATION & LEARNING (MEL)

7.1 Evaluation Design

Mixed-methods quasi-experimental implementation science study with matched comparison design. Three pilot districts matched with three comparison districts on key demographic and health indicators. Comparison districts receive standard care (existing iCHIS/DHIS2 without AI augmentation).

Primary Outcomes: 1. Maternal Health: Proportion of high-risk pregnancies identified before 32 weeks; proportion of maternal complications reaching facilities as emergencies; maternal mortality ratio. 2. Child Health: Proportion of under-5 danger signs correctly identified and referred; under-5 mortality rate; case fatality rate for severe malaria, pneumonia, diarrhea. 3. Surveillance: Timeliness of outbreak detection (days from index case to official alert); accuracy of outbreak prediction (sensitivity, specificity, PPV, NPV); proportion of predicted outbreaks with pre-positioned supplies. 4. Supply Chain: Medicine stockout duration; proportion of stockouts predicted ≥4 weeks in advance; proportion of referrals matched to facilities with required medicines.

Secondary Outcomes: - CHW workload and job satisfaction - Community trust and acceptability - Cost-effectiveness (cost per DALY averted) - Policy adoption metrics

Qualitative Methods: - In-depth interviews with 45 CHWs, 15 nurses, 9 DHO staff, 15 community leaders, 10 MoHP policymakers. - Focus group discussions with pregnant women and mothers of under-5s. - Ethnographic observation of CHW home visits and DHO outbreak response meetings. - Document analysis of policy briefs, parliamentary records, and budget documents.

7.2 MEL Framework

| Level | Indicator | Data Source | Frequency |
| --- | --- | --- | --- |
| Process | % CHWs actively using MAMA-AI | Platform analytics | Weekly |
|  | % alerts responded to within 24 hours | Platform analytics + DRRT records | Real-time |
|  | Model accuracy (AUC-ROC, precision, recall) | Validation datasets | Monthly |
| Outcome | High-risk pregnancy identification rate | iCHIS + MAMA-AI data | Monthly |
|  | Outbreak detection timeliness | PHIM surveillance records | Per outbreak |
|  | Stockout prediction accuracy | LMIS + CHUMA-AI data | Monthly |
| Impact | Maternal mortality ratio | DHIS2 + verbal autopsy | Quarterly |
|  | Under-5 mortality rate | DHIS2 | Quarterly |
|  | Policy adoption score | Document review | Semi-annually |

8. SUSTAINABILITY & SCALE-UP PLAN

8.1 Financial Sustainability

Year 1–2: 100% grant-funded ($9.85M).

Year 3 onwards: Transition to blended financing: - Government budget: MoHP commits to absorbing platform maintenance, cloud hosting, and CHW device replacement costs. - World Bank GESD 2.0: AI-predicted health targets incorporated into Performance-Based Grants. - Domestic resource mobilization: Business case presented to Ministry of Finance for MTEF inclusion.

8.2 Technical Sustainability

- Local capacity building: Train 10 Malawian data scientists and software engineers, establishing a Malawi National AI Health Lab within PHIM.

- Open-source commitment: All non-proprietary code released under MIT license.

- DHIS2 ecosystem alignment: Leverages the world’s largest open-source health information system community.

8.3 Institutional Sustainability

- Policy anchoring: National AI in Health Policy Framework institutionalizes governance structures.

- Scale-up roadmap: District-by-district rollout approved by MoHP Cabinet Committee by Month 30.

9. RISK ANALYSIS & MITIGATION

| Risk | Likelihood | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| Competitor establishes market position first | Medium | High | Accelerate pilot deployment; emphasize integration moat; secure exclusive MoHP data sharing agreements |
| CHW resistance to AI tools | Medium | High | Extensive co-design; peer champion model; clear messaging that AI supports (not replaces) CHW judgment |
| Model bias against marginalized groups | Medium | Very High | Proactive bias auditing; stratified training data; community advisory boards; quarterly Ethics Committee review |
| Connectivity failures in rural areas | High | Medium | Offline-first architecture; edge computing; SMS/USSD fallback |
| Government transition delays | Medium | High | Early engagement of Ministry of Finance; embed in National Health Policy implementation framework |
| Data privacy breaches | Low | Very High | End-to-end encryption; de-identification; compliance with Data Protection Act; independent security audits |
| Outbreak prediction false alarms | Medium | Medium | Calibrated alert thresholds with human verification; DRRT feedback loops; continuous model refinement |
| Political transition disrupting policy pathway | Medium | High | Bipartisan engagement; anchor in civil service (PHIM) rather than political appointees |

10. DETAILED BUDGET FRAMEWORK (36 MONTHS)

10.1 Budget Summary by Category

| Budget Category | Year 1 (USD) | Year 2 (USD) | Year 3 (USD) | Total (USD) | % of Total |
| --- | --- | --- | --- | --- | --- |
| Personnel | 1,485,000 | 1,620,000 | 1,485,000 | 4,590,000 | 46.6% |
| Technology & Infrastructure | 1,120,000 | 680,000 | 420,000 | 2,220,000 | 22.5% |
| Operations & Implementation | 580,000 | 620,000 | 440,000 | 1,640,000 | 16.6% |
| Monitoring, Evaluation & Research | 420,000 | 380,000 | 280,000 | 1,080,000 | 11.0% |
| Policy & Scale-Up | 80,000 | 120,000 | 120,000 | 320,000 | 3.3% |
| TOTAL | 3,685,000 | 3,420,000 | 2,745,000 | 9,850,000 | 100% |

10.2 Detailed Line-Item Budget

CATEGORY A: PERSONNEL ($4,590,000)

A.1 International Technical Assistance

| Position | FTE | Year 1 | Year 2 | Year 3 | Total | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| Project Director (International) | 1.0 | 180,000 | 180,000 | 150,000 | 510,000 | Senior health systems/AI specialist; 20% time in Year 3 |
| Chief Technical Officer (International) | 1.0 | 160,000 | 160,000 | 130,000 | 450,000 | Platform architecture, AI/ML engineering, security |
| Implementation Science Lead (International) | 0.5 | 70,000 | 70,000 | 50,000 | 190,000 | Mixed-methods evaluation design, PhD-level epidemiologist |
| AI Ethics Advisor (International) | 0.25 | 35,000 | 35,000 | 25,000 | 95,000 | Bioethicist with LMIC AI experience |
| Subtotal International TA |  | 445,000 | 445,000 | 355,000 | 1,245,000 |  |

A.2 National Staff (Malawi-based)

| Position | FTE | Year 1 | Year 2 | Year 3 | Total | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| Deputy Project Director (National) | 1.0 | 75,000 | 80,000 | 80,000 | 235,000 | Senior Malawian health systems expert; assumes PD role in Year 3 |
| MAMA-AI Program Manager | 1.0 | 55,000 | 60,000 | 60,000 | 175,000 | CHW program specialist, clinical background |
| ULALO-AI Program Manager | 1.0 | 55,000 | 60,000 | 60,000 | 175,000 | Surveillance/epidemiology background |
| CHUMA-AI Program Manager | 1.0 | 55,000 | 60,000 | 60,000 | 175,000 | Supply chain/health economics background |
| Software Engineering Lead | 1.0 | 65,000 | 70,000 | 70,000 | 205,000 | Full-stack + mobile development |
| ML/Data Science Lead | 1.0 | 65,000 | 70,000 | 70,000 | 205,000 | Model development, validation, retraining |
| DHIS2 Integration Specialist | 1.0 | 55,000 | 60,000 | 60,000 | 175,000 | DHIS2 API, iCHIS/CHT expertise |
| MEL Manager | 1.0 | 50,000 | 55,000 | 55,000 | 160,000 | Monitoring, evaluation, data quality |
| Research Coordinator | 1.0 | 45,000 | 50,000 | 50,000 | 145,000 | Qualitative research, ethics coordination |
| Finance & Admin Manager | 1.0 | 45,000 | 50,000 | 50,000 | 145,000 | Grant compliance, procurement, HR |
| District Coordinators (3) | 3.0 | 90,000 | 90,000 | 90,000 | 270,000 | One per pilot district |
| CHW Supervisors (9) | 9.0 | 180,000 | 180,000 | 180,000 | 540,000 | 3 per district |
| Data Clerks (6) | 6.0 | 72,000 | 72,000 | 72,000 | 216,000 | Data entry, cleaning, DHIS2 support |
| Communications Officer | 0.5 | 20,000 | 22,000 | 22,000 | 64,000 | Policy communications, community engagement |
| Subtotal National Staff |  | 927,000 | 1,029,000 | 1,029,000 | 2,985,000 |  |

A.3 Short-Term Consultants

| Role | Days/Year | Year 1 | Year 2 | Year 3 | Total | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| HCD/UX Design Consultant | 60 | 30,000 | 15,000 | 10,000 | 55,000 | Human-centered design for CHW app |
| Health Economics Consultant | 30 | 20,000 | 20,000 | 15,000 | 55,000 | Cost-effectiveness analysis |
| Climate Data Scientist | 30 | 18,000 | 18,000 | 12,000 | 48,000 | Climate-health model calibration |
| Policy Advocacy Consultant | 20 | 10,000 | 15,000 | 15,000 | 40,000 | Parliamentary engagement |
| Security Audit Consultant | 15 | 15,000 | 10,000 | 10,000 | 35,000 | Annual penetration testing |
| Biostatistician | 30 | 20,000 | 18,000 | 14,000 | 52,000 | Advanced statistical analysis |
| Subtotal Consultants |  | 113,000 | 96,000 | 76,000 | 285,000 |  |

A.4 Training & Capacity Building

| Activity | Year 1 | Year 2 | Year 3 | Total | Notes |
| --- | --- | --- | --- | --- | --- |
| Local data scientist training (10 fellows, 6-month program) | 50,000 | 50,000 | 40,000 | 140,000 | Fellowship within PHIM AI Health Lab |
| CHW refresher training (450 CHWs x 3 sessions) | 45,000 | 30,000 | 20,000 | 95,000 | Per diems, transport, materials |
| DHO staff training (3 districts x 15 staff) | 20,000 | 15,000 | 10,000 | 45,000 | Dashboard use, alert response |
| MoHP policymaker workshops | 15,000 | 15,000 | 10,000 | 40,000 | AI literacy, dashboard interpretation |
| International conference attendance (5 staff) | 25,000 | 20,000 | 15,000 | 60,000 | Global health/AI conferences |
| Subtotal Training |  | 155,000 | 130,000 | 95,000 | 380,000 |

CATEGORY A TOTAL: $4,590,000

CATEGORY B: TECHNOLOGY & INFRASTRUCTURE ($2,220,000)

B.1 Software Development

| Component | Year 1 | Year 2 | Year 3 | Total | Notes |
| --- | --- | --- | --- | --- | --- |
| MAMA-AI mobile app development | 180,000 | 60,000 | 30,000 | 270,000 | Android (Kotlin), offline-first, CHT-compatible |
| ULALO-AI analytics pipeline | 150,000 | 50,000 | 25,000 | 225,000 | Cloud ETL, time-series, spatial clustering |
| CHUMA-AI supply chain module | 120,000 | 40,000 | 20,000 | 180,000 | LMIS integration, demand forecasting |
| Ministerial dashboard (web) | 100,000 | 30,000 | 15,000 | 145,000 | React/Angular, NLG summaries |
| DHIS2/iCHIS/LMIS API integration | 80,000 | 30,000 | 15,000 | 125,000 | Bidirectional sync, data mapping |
| Edge AI model optimization | 60,000 | 20,000 | 10,000 | 90,000 | TensorFlow Lite, on-device inference |
| Security & encryption modules | 50,000 | 20,000 | 10,000 | 80,000 | End-to-end encryption, auth, audit |
| UX/UI design system | 40,000 | 15,000 | 5,000 | 60,000 | Design system for all interfaces |
| Subtotal Software Dev |  | 780,000 | 265,000 | 130,000 | 1,175,000 |

B.2 Cloud Infrastructure & Hosting

| Service | Year 1 | Year 2 | Year 3 | Total | Notes |
| --- | --- | --- | --- | --- | --- |
| Cloud compute (AWS/Azure/GCP) | 60,000 | 70,000 | 75,000 | 205,000 | Model training, analytics, dashboards |
| Data storage & backup | 25,000 | 30,000 | 35,000 | 90,000 | Encrypted, disaster recovery |
| CDN & edge caching | 10,000 | 12,000 | 15,000 | 37,000 | Low-latency dashboard access |
| SMS gateway services | 15,000 | 18,000 | 20,000 | 53,000 | Fallback alerts, CHW reminders |
| API & integration licenses | 10,000 | 12,000 | 12,000 | 34,000 | Climate data APIs, mapping |
| Subtotal Cloud |  | 120,000 | 142,000 | 157,000 | 419,000 |

B.3 Hardware & Devices

| Item | Qty | Unit Cost | Year 1 | Year 2 | Year 3 | Total | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Smartphones for CHWs | 450 | $180 | 81,000 | 27,000 | 18,000 | 126,000 | Ruggedized Android; 30% replacement annually |
| Tablets for DHOs | 15 | $300 | 4,500 | 1,500 | 1,500 | 7,500 | District-level dashboard access |
| Laptops for MoHP/PHIM | 10 | $800 | 8,000 | 0 | 4,000 | 12,000 | Ministerial dashboard, research |
| Solar chargers for CHWs | 450 | $25 | 11,250 | 3,750 | 3,750 | 18,750 | Essential for rural electricity gaps |
| Portable routers (MiFi) | 30 | $80 | 2,400 | 800 | 800 | 4,000 | DHO connectivity backup |
| Server hardware (on-premise backup) | 1 | 15,000 | 15,000 | 0 | 0 | 15,000 | Government data sovereignty |
| Subtotal Hardware |  |  | 122,150 | 33,050 | 28,050 | 183,250 |  |

B.4 Connectivity & Communications

| Item | Year 1 | Year 2 | Year 3 | Total | Notes |
| --- | --- | --- | --- | --- | --- |
| Mobile data bundles (450 CHWs x 12 months) | 54,000 | 54,000 | 54,000 | 162,000 | Monthly data allowances |
| Internet for project offices | 18,000 | 18,000 | 18,000 | 54,000 | 3 districts + Lilongwe |
| Satellite internet backup (2 remote sites) | 8,000 | 8,000 | 8,000 | 24,000 | Neno and Nsanje redundancy |
| Subtotal Connectivity |  | 80,000 | 80,000 | 80,000 | 240,000 |

B.5 Software Licenses & Tools

| Item | Year 1 | Year 2 | Year 3 | Total | Notes |
| --- | --- | --- | --- | --- | --- |
| DHIS2 customization & support | 25,000 | 25,000 | 25,000 | 75,000 | AI integration customization |
| CHT platform support | 15,000 | 15,000 | 15,000 | 45,000 | CHT technical support |
| ML/Analytics tools | 20,000 | 20,000 | 20,000 | 60,000 | Python, GIS, NLG libraries |
| Project management tools | 8,000 | 8,000 | 8,000 | 24,000 | Jira, Slack, Miro |
| Subtotal Licenses |  | 68,000 | 68,000 | 68,000 | 204,000 |

CATEGORY B TOTAL: $2,220,000

CATEGORY C: OPERATIONS & IMPLEMENTATION ($1,640,000)

C.1 Community Engagement & Mobilization

| Activity | Year 1 | Year 2 | Year 3 | Total | Notes |
| --- | --- | --- | --- | --- | --- |
| Community sensitization meetings | 45,000 | 30,000 | 20,000 | 95,000 | 3 districts x 20 meetings |
| Radio & community media campaigns | 30,000 | 20,000 | 15,000 | 65,000 | Local radio, community theater |
| Feedback mechanisms | 10,000 | 8,000 | 5,000 | 23,000 | Suggestion boxes, hotlines |
| Subtotal Community Engagement |  | 85,000 | 58,000 | 40,000 | 183,000 |

C.2 Travel & Transportation

| Activity | Year 1 | Year 2 | Year 3 | Total | Notes |
| --- | --- | --- | --- | --- | --- |
| Vehicle leasing (4WD, 6 vehicles) | 72,000 | 72,000 | 60,000 | 204,000 | Essential for rural access |
| Fuel & maintenance | 48,000 | 48,000 | 40,000 | 136,000 |  |
| Air travel (international staff, conferences) | 35,000 | 30,000 | 20,000 | 85,000 |  |
| Local transport (motorcycles for supervisors) | 24,000 | 18,000 | 12,000 | 54,000 | 9 motorcycles |
| Per diems & accommodation | 40,000 | 35,000 | 25,000 | 100,000 |  |
| Subtotal Travel |  | 219,000 | 203,000 | 157,000 | 579,000 |

C.3 Workshops & Meetings

| Activity | Year 1 | Year 2 | Year 3 | Total | Notes |
| --- | --- | --- | --- | --- | --- |
| Co-design workshops (HCD) | 35,000 | 10,000 | 5,000 | 50,000 | Human-centered design |
| Quarterly PSC meetings | 15,000 | 15,000 | 12,000 | 42,000 | Project Steering Committee |
| Annual review & planning | 20,000 | 20,000 | 15,000 | 55,000 | Consortium-wide |
| District coordination meetings | 18,000 | 18,000 | 12,000 | 48,000 | Monthly DHO coordination |
| Policy workshops & parliamentary briefings | 10,000 | 15,000 | 15,000 | 40,000 | Policy engagement |
| Subtotal Workshops |  | 98,000 | 78,000 | 59,000 | 235,000 |

C.4 Office & Administrative Costs

| Item | Year 1 | Year 2 | Year 3 | Total | Notes |
| --- | --- | --- | --- | --- | --- |
| Office rent (Lilongwe + 3 districts) | 36,000 | 36,000 | 30,000 | 102,000 |  |
| Office equipment & furniture | 25,000 | 10,000 | 5,000 | 40,000 |  |
| Utilities & communications | 18,000 | 18,000 | 15,000 | 51,000 |  |
| Insurance | 20,000 | 20,000 | 18,000 | 58,000 | Project, liability, cyber |
| Printing, stationery, supplies | 12,000 | 10,000 | 8,000 | 30,000 |  |
| Security | 8,000 | 8,000 | 6,000 | 22,000 |  |
| Subtotal Office & Admin |  | 119,000 | 102,000 | 82,000 | 303,000 |

C.5 CHW Incentives & Support

| Item | Year 1 | Year 2 | Year 3 | Total | Notes |
| --- | --- | --- | --- | --- | --- |
| CHW performance incentives | 120,000 | 120,000 | 80,000 | 320,000 | Monthly top-ups for active users |
| CHW peer support networks | 15,000 | 12,000 | 8,000 | 35,000 | WhatsApp groups, peer learning |
| CHW protective equipment | 20,000 | 15,000 | 10,000 | 45,000 | Bags, raincoats, first aid kits |
| Subtotal CHW Support |  | 155,000 | 147,000 | 98,000 | 400,000 |

CATEGORY C TOTAL: $1,640,000

CATEGORY D: MONITORING, EVALUATION & RESEARCH ($1,080,000)

D.1 Baseline & Endline Surveys

| Activity | Year 1 | Year 2 | Year 3 | Total | Notes |
| --- | --- | --- | --- | --- | --- |
| Household baseline survey | 85,000 | 0 | 0 | 85,000 | 1,200 households; 3 pilot + 3 comparison |
| Household endline survey | 0 | 0 | 75,000 | 75,000 | Same sampling frame |
| Midline survey | 0 | 65,000 | 0 | 65,000 | Rapid assessment at Month 18 |
| Subtotal Surveys |  | 85,000 | 65,000 | 75,000 | 225,000 |

D.2 Qualitative Research

| Activity | Year 1 | Year 2 | Year 3 | Total | Notes |
| --- | --- | --- | --- | --- | --- |
| In-depth interviews (120 participants) | 30,000 | 25,000 | 20,000 | 75,000 | CHWs, nurses, DHO staff, policymakers |
| Focus group discussions (24 FGDs) | 25,000 | 20,000 | 15,000 | 60,000 | Pregnant women, mothers |
| Ethnographic observation | 20,000 | 20,000 | 15,000 | 55,000 | 6-month embedded per district |
| Transcription & translation | 15,000 | 12,000 | 10,000 | 37,000 | Chichewa/English |
| Subtotal Qualitative |  | 90,000 | 77,000 | 60,000 | 227,000 |

D.3 Health Facility Assessments

| Activity | Year 1 | Year 2 | Year 3 | Total | Notes |
| --- | --- | --- | --- | --- | --- |
| Facility readiness assessments | 35,000 | 30,000 | 25,000 | 90,000 | 45 facilities x 3 rounds |
| Quality of care observations | 20,000 | 18,000 | 15,000 | 53,000 | Clinical audits, patient flow |
| Subtotal Facility Assessments |  | 55,000 | 48,000 | 40,000 | 143,000 |

D.4 Data Systems & Analytics

| Activity | Year 1 | Year 2 | Year 3 | Total | Notes |
| --- | --- | --- | --- | --- | --- |
| Platform analytics setup | 25,000 | 15,000 | 10,000 | 50,000 | Automated MEL dashboards |
| External evaluation | 30,000 | 30,000 | 25,000 | 85,000 | Independent impact evaluation |
| Model validation & bias auditing | 20,000 | 20,000 | 15,000 | 55,000 | External ML fairness audit |
| Data quality assurance | 15,000 | 12,000 | 10,000 | 37,000 | Routine verification |
| Subtotal Data Systems |  | 90,000 | 77,000 | 60,000 | 227,000 |

D.5 Knowledge Products & Dissemination

| Activity | Year 1 | Year 2 | Year 3 | Total | Notes |
| --- | --- | --- | --- | --- | --- |
| Peer-reviewed publications (3-5 papers) | 15,000 | 20,000 | 15,000 | 50,000 | Open access fees |
| Policy briefs & reports | 10,000 | 12,000 | 10,000 | 32,000 |  |
| Implementation toolkit | 0 | 15,000 | 10,000 | 25,000 | Open-source adaptation guide |
| Southern Africa AI in Health Symposium | 0 | 0 | 35,000 | 35,000 | Regional knowledge sharing |
| Conference presentations | 10,000 | 8,000 | 6,000 | 24,000 |  |
| Subtotal Knowledge Products |  | 35,000 | 55,000 | 76,000 | 166,000 |

D.6 Ethics & Regulatory

| Activity | Year 1 | Year 2 | Year 3 | Total | Notes |
| --- | --- | --- | --- | --- | --- |
| NHSRC ethics review fees | 5,000 | 3,000 | 2,000 | 10,000 |  |
| Ethics Committee operations | 15,000 | 12,000 | 10,000 | 37,000 | Quarterly meetings |
| Community advisory board | 8,000 | 8,000 | 6,000 | 22,000 | Community representation |
| Subtotal Ethics |  | 28,000 | 23,000 | 18,000 | 69,000 |

CATEGORY D TOTAL: $1,080,000

CATEGORY E: POLICY & SCALE-UP ($320,000)

| Activity | Year 1 | Year 2 | Year 3 | Total | Notes |
| --- | --- | --- | --- | --- | --- |
| National AI in Health Policy drafting | 20,000 | 30,000 | 25,000 | 75,000 | Legal drafting, consultations |
| Parliamentary engagement | 15,000 | 20,000 | 20,000 | 55,000 | Committee hearings, MP briefings |
| National Commission for Science & Technology | 10,000 | 15,000 | 15,000 | 40,000 | Regulatory framework |
| Scale-up plan development | 10,000 | 20,000 | 20,000 | 50,000 | District-by-district rollout |
| Government transition support | 0 | 15,000 | 20,000 | 35,000 | MoHP absorption |
| Regional replication workshops | 0 | 10,000 | 10,000 | 20,000 | Support other LMICs |
| Policy communications campaign | 10,000 | 10,000 | 10,000 | 30,000 | Media, advocacy |
| CATEGORY E TOTAL |  | 65,000 | 120,000 | 135,000 | 320,000 |

CATEGORY F: INDIRECT COSTS & CONTINGENCY

Indirect costs calculated at 7% of direct costs ($9,850,000 x 0.07 = $689,500), absorbed within line-item budgets. A 5% contingency ($492,500) is embedded within operational and technology categories.

10.3 Budget by Engine & Cross-Cutting

| Component | Year 1 | Year 2 | Year 3 | Total | % of Total |
| --- | --- | --- | --- | --- | --- |
| MAMA-AI (Maternal-Child Health) | 1,180,000 | 1,050,000 | 850,000 | 3,080,000 | 31.3% |
| ULALO-AI (Surveillance) | 980,000 | 900,000 | 720,000 | 2,600,000 | 26.4% |
| CHUMA-AI (Supply Chain & Policy) | 820,000 | 820,000 | 680,000 | 2,320,000 | 23.5% |
| Cross-Cutting (MEL, Policy, Management) | 705,000 | 650,000 | 495,000 | 1,850,000 | 18.8% |
| TOTAL | 3,685,000 | 3,420,000 | 2,745,000 | 9,850,000 | 100% |

10.4 Cost-Effectiveness Projection

| Outcome | Projected Impact (3 Years) | Cost per Outcome |
| --- | --- | --- |
| Maternal deaths averted | 180-240 | $41,000-$55,000 per death averted |
| Under-5 deaths averted | 450-600 | $16,000-$22,000 per death averted |
| Outbreaks detected >=2 weeks earlier | 8-12 | $820,000-$1,230,000 per outbreak |
| Stockout-days prevented | 15,000-20,000 | $490-$660 per stockout-day prevented |
| DALYs averted (total) | 25,000-35,000 | $280-$390 per DALY |

Note: Cost per DALY averted of $280-$390 is highly cost-effective by WHO thresholds (1-3x GDP per capita = $330-$990 for Malawi).

11. ANNEXES

Annex A: Letters of Support

- Letter from Principal Secretary, Ministry of Health and Population

- Letter from Director General, Public Health Institute of Malawi

- Letter from Dean, University of Malawi College of Medicine

- Letters from District Commissioners, Nsanje, Neno, and Blantyre

Annex B: Organizational Capacity Statements

- Partners In Health – Malawi: 15 years of health system strengthening

- VillageReach: Digital health infrastructure expertise across 15 African countries

- PHIM / College of Medicine: National research and surveillance leadership

Annex C: Draft Data Sharing Agreement

- MoU between consortium and MoHP governing data access, privacy, and AI model governance

Annex D: AI Ethics Framework (Draft)

- Principles, governance structure, bias audit protocol, accountability mechanisms

Annex E: Risk Matrix (Expanded)

- Full risk register with probability/impact scoring and detailed mitigation plans

Annex F: Implementation Timeline (Gantt Chart)

- Month-by-month activity schedule for all 36 months

Annex G: Personnel CVs

- Key personnel resumes

Annex H: Competitive Landscape Documentation

- Evidence of existing competitors (HISP UNIMA/GIZ, EVAH, VillageReach, Kenya CHP AI, etc.)

- Differentiation analysis for each competitor

CONCLUSION

Zisamale does not claim to be the first AI health platform in Malawi. We acknowledge that HISP UNIMA and GIZ are already deploying predictive surveillance, that EVAH-funded projects are evaluating CHW AI tools, and that VillageReach is optimizing supply chains with AI.

Our claim is different: We are the first to build the integrated system that closes the loop between prediction, community action, supply chain response, and national policy governance. We are the first to build the institutional infrastructure — the ethics committee, the national AI lab, the policy framework, the trained local workforce — that makes AI permanent in Malawi’s health system.

The AI is the engine. Zisamale is building the car, the road, the driver’s license system, the traffic laws, and the mechanic’s shop. No one else is doing that — because no one else has been here long enough.

We respectfully request $9,850,000 over 36 months to make this vision a reality.

Prepared by the Zisamale Consortium
Lilongwe, Malawi
August 2026